**Case Study: Scheduling via MS Project (Bonus)**

Early Start (ES)

Early Finish (EF)

Late Start (LS)

Late Finish (LF)

Duration

Float

|  |  |  |
| --- | --- | --- |
| ES | AN | EF |
| LS | DU | LF |

AN = Activity Name

DU = Duration

ES = Early start

EF = Early finish

LS = Late start

LF = Late finish

|  |  |  |
| --- | --- | --- |
| 3 | B | 7 |
| 3 | 4 | 7 |

|  |  |  |
| --- | --- | --- |
| 7 | D | 12 |
| 7 | 5 | 12 |

|  |  |  |
| --- | --- | --- |
| 12 | G | 16 |
| 12 | 4 | 16 |

|  |  |  |
| --- | --- | --- |
| 5 | E | 6 |
| 11 | 1 | 12 |

|  |  |  |
| --- | --- | --- |
| 0 | A | 3 |
| 0 | 3 | 3 |

|  |  |  |
| --- | --- | --- |
| 3 | C | 5 |
| 9 | 2 | 11 |

|  |  |  |
| --- | --- | --- |
| 16 | H | 19 |
| 16 | 3 | 19 |

|  |  |  |
| --- | --- | --- |
| 5 | F | 7 |
| 14 | 2 | 16 |

**This project has a duration of 19 days**