## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account | As a user, I want to create an account so that I can start using the app | High | Yes | 1 | To do
|  | As a user, I want to log in so that I can access to my account | High | Yes | 1 | To do
| View Restaurants | As a user, I want to view restaurants so that I can see all available restaurants | High | Yes | 1 | To do
| Search Restaurants | As a user, I want to decide which restaurant I want so that I can order food | High | Yes | 1 | To do
| View Menu | As a user, I want to view the menu for a selected restaurant so that I can see the item's price | High | Yes | 2 | To do
| Add to Cart | As a user, I want to add the food that I want to the cart so that I can complete the purchase process | High | Yes | 2 | To do
| Purchase | As a user, I want to select the type of payment so that I can choose the right payment method for me | Meduim | Yes | 3 | To do
|  | As a user, I want to select a payment method like ApplePay, CreditCard, Talabat pay, or cash on delivery | Meduim | Yes | 3 | To do
|  | As a user, I want to decide if I want to give the driver some money so that I can choose 2 dirhams for ice cream or 4 dirhams for fries, or any other amount | Meduim | Yes | 3 | To do
|  | As a user, I want to use a promo code so that I can have a discount | Meduim | Yes | 3 | To do
| Restaurant views order | As a restaurant, I want to view customer orders so that I can prepare it | Meduim | Yes | 4 | To do
| Restaurant marks order as delivered | As a restaurant, I want to mark an order as delivered so that I can remove it from the orders list | Meduim | Yes | 4 | To do